## Quiz 1
Questions | Options
Question 1:
A Program can best be described in which of the following ways?
A very large, complex project
A collection of sub-projects with a common goal
A collection of projects structured to provide efficiency gains
A collection of subprojects with a common customer
Question 2:
All of the following characteristics flow from Portfolio to Program except
Strategy and Priorities
Progressive elaboration
Governance
Tactical priorities
Question 3:
Business Value creation is the combination of tangible and Intangible assets. Which one is an intangible asset
Monetary assets
Stakeholder equity
Utility
Brand recognition
Question 4:
If the relationship among the components is one of only with a shared client, Seller, Technology, or Resource, it should be managed as
Program
Portfolio
Operation
Project
Question 5:
Compliance Programs is initiated as a result of
Process Improvement Initiatives
New Product introduction due to market demand
Data Privacy and security requirements
New Service launch to cater to traffic congestion

## Quiz 2
Questions
Question 1:
You are a program manager for a software services company. This new software will bring your company into Cloud computing. It also will replace your company's legacy finance and accounting systems. You are to complete your program in two years. Your sponsor has asked you to develop metrics for program success. This is done as part of the development of the -
Program charter
Program roadmap
Program mandate
Program management plan
Question 2:
You are a functional manager in your organization, the head of the Department of Engineering and a member of the Selection Committee for new programs. At the committee meetings, you review potential programs. One key factor that you consider as to whether to approve a program is -
Who will be the program manager?
What are the funding requirements?
What is the source of program funding?
What are the next steps to get the program started?
Question 3:
John is the Program Manager for a new Emergent program which is expected to bring process improvements across the organization. His sponsor asks him to create a Program charter for this new program. Which of the following, his Program Charter must contain :
Values, goals & objectives
Strategies, benefit realization plan
Benefits realization plan, objectives
Vision, Justification and Strategic fit
Question 4:
Nancy is in the process of creating Business Case to justify the necessity to initiate the Program ABC. This program is anticipated to Increase the market share for most of the products which are produced by your Organization in future. Which of the following, Nancy will consider least for creating her Business Case in this Program?
Net Present Value
IRR
Earned Value
Cost Benefit analysis
Question 5:
Assume you are working to change the culture of your organization to one that views its programs and projects as strategic assets and critical to overall success. You have been working on a team to define the long term objectives of the organization and to set forth vision and mission statements for employees that are meaningful and informative. In your efforts you recognize and your team has agreed that one of the indicators of the organization's risk tolerance is found in its -
Program management office
Portfolio
Strategic plan
Program charter
Question 6:
Assume you are working to change the culture of your organization to one that views its programs and projects as strategic assets and critical to overall success. You have been working on a team to define the long-term objectives of the organization and to set forth vision and mission statements for employees that are meaningful and informative. In your efforts you recognize and your team has agreed that one of the truest measures of an organization's intent, direction, and progress is found in its:
PMO-Program Management Office
Portfolio Office Charter
Program Charter
None of the above

## Quiz 3
Questions
Question 1:
Stella is managing a program to develop a new product to protect all workers from air/water borne diseases at the workplace to assure everyone that the workplace is clean. They will not have to unduly worry in the future if a co-worker has communicable disease. However, you have just learned that there was a failure to adhere to a major element in the work breakdown structure (WBS) of one of the key projects. The solution to this problem is :
Interactions and realignment of this project must be managed
Re-baselining may be required
A change request has been approved
New metrics are required
Question 2:
As the manager of a new program to develop the next generation heating, ventilation and air-conditioning (HVAC) system, you have three projects in your program. This is the first year and you expect the program to last at least three years and are hopeful of PMO support. You also are sure more projects will be added as the program ensues. Therefore, you establish a process to monitor your program benefits. Following the standard benefits management life cycle, you develop this process during the -
Benefits identification
Benefits analysis and planning
Benefits realization
Benefits delivery
Question 3:
You are the program manager for the development of a new slot machine for the Sand Dunes casino in Macau. Your company is using program management more frequently as it realizes the benefits associated with it but operate with a balanced matrix structure. You meet regularly with members of your Governance Board for periodic health checks, which provide the Board an opportunity to
Formally review program performance
Assess progress toward benefit realization and sustainment
Focus on the phase that was just completed to determine whether the next phase should begin
Review and approve required program changes
Question 4:
You are a program manager for your organization. Your program will include seventeen projects over the life of the program. You may create a component project at any time in a program except for during what time of the program?
Initiating
Closing
Monitoring and controlling
Planning
Question 5:
As the program manager for a new pipeline system that has its goal no potential incidents of any type, you have a major challenge as your company in the past has had a poor safety record. This program is complex and this goal will be difficult to achieve. However, after working to plan the program for three years, your Steering Committee met and approved your program management plan. As you move to approve components to be part of your program, you need to review the
Component Charter
Change Control
Business Plan
Program Management plan
Question 6:
Program management processes are
Standard
Overlapping
Iterative
Mutually Exclusive

## Quiz 4
Question 1:
You will be appointed as a Program Manager for a city Metro transport system. Metro is going to bring big relief to traffic congestions in the city and change the way, the people live. Finally, your program charter was approved and you were officially named as the program manager. You were fortunate to work with your sponsor in developing the charter and you also -
Used input from all stakeholders
Relied extensively on historical information
Convened a panel to assist in its preparation using the Delphi technique
Sent a draft of the charter to the proposed members of the Governance Board for their input
Question 2:
It is the first time you are managing a program. You have successfully managed several projects and you are on a career path that now leads to program management. On your program, you want to apply some of the successful best practices for your projects, recognizing the differences between programs and projects and their greater complexity. However, since you have been in project management for long now in this company, therefore
You need to prepare a comprehensive WBS for the program that includes the work of the projects
You want to build your program schedule only after all the project schedules are complete
You recognize the importance of qualifying and quantifying all possible risks
You realize project stakeholders are also program stakeholders
Question 3:
You are appointed as a Program Manager for the 2 Billion USD Program for an Engineering Company. Within your program, there are lots of procurements planned and those procurements will be reviewed by Purchasing team which needs budget approval by Finance team and later, the end product will be marketed by Marketing Department. You are planning to issue a RFP for some of the procurements which are planned. At this point in time, which of the below stakeholders will you focus more during this process?
Purchasing department who will process the RFP
Marketing department who will market the product
The stakeholder from whom you expect a response for the RFP
Finance department who will fund the RFP
Question 4:
Your program team is ready to fly to Europe as a part of Program implementation. At the last moment, you notice that the finance team has not approved the cost of their fares. Hence the tour had to be cancelled since the Finance team was not aware that such a travel has been scheduled. What would have been the probable cause of this issue?
Finance team was not identified as a stakeholder & not updated in stakeholder management plan
Finance team was not identified as a stakeholder & not updated in program management plan
Travel information should have been communicated to finance department and necessary approvals should have been received well in advance
Finance team was not identified as a stakeholder & not updated in Communication management plan
Question 5:
You are a program manager for a city transport corporation. The program has a number of projects under way to upgrade the existing infrastructure to new technologies and also to implement a process improvement program. The transit authority's chief financial officer has left the organisation to assume a position in a different city and a new person has been appointed. You should -
Update your stakeholder inventory
Appoint one of your core team members to interact with the new CFO
Update the stakeholder register
Meet with the new CFO to explain the importance of the program

## Quiz 5
Question 1:
As a risk expert, you have been requested by the program Governance Board to perform a risk assessment for their important program, which includes more than 25 projects. The focus of your assessment should be on -
Analysing response mechanisms for individual components
Ensuring that each project has a risk mitigation plan
Inter projects risks
Stakeholder risk tolerance and thresholds
Question 2:
Within the Era steel, management uses the terms project management and program management interchangeably and there is no consistency across programs. Furthermore, there is no executive support to facilitate issue resolution, no direction or leadership provided to program teams and little control over work initiatives. As an external consultant, you have been asked to provide recommendations for improvement. You prepare a report with a prioritized list of actions for Era Steel. On top of the list is
A portfolio management information system
Enterprise project management across all divisions
A program governance model
A program delivery model is responsible for supporting competencies
Question 3:
An organization that program governance, adherence to standards, developing and institutionalizing processes, procedures and templates is
Quality Assurance
Program Management Office
Governance Boards
Steering Committee
Question 4:
Which stakeholder in an organization assigns responsibility to the project manager of a project within a program?
Program director
Program customer
Program sponsor
Program manager
Question 5:
Members of your program governance board are complaining about performance information from your program. They claim that your reports are too detailed, are too many in number, and are produced on a shifting schedule. You met with each person on the board early in the program and thought you were meeting their information requirements. You then asked your organization's Enterprise PMO for assistance. The Enterprise PMO Director recommends the development and use of
Dashboard
Industry Metrics
Executive Summary
Interview and Face to face meeting

## Quiz 6
Question 1:
As Nancy works on an emergency response program for the city, It is recognized that one will need a number of different types of supplies and services to support the program and its component projects. One common approach is to use -
Expert judgment
Formalized proposal evaluation criteria
Screening systems
Screening systems
Question 2:
As a program manager on a multiyear, multimillion dollar transportation program for the provincial government. Funding for your program is allocated on a fiscal year basis, yet your program will continue for multiple years. This arrangement will affect how your costs are -
Estimated
Obligated
Committed
Budgeted
Question 3:
You establish a program support function to provide ongoing product support for the heating, ventilating and air-conditioning program for the new class of amphibious warfare vehicles. Prior to transitioning your program's work to this group, you need to ensure -
Successful, on-time product delivery
That the Program is accepted and closed
That attention is paid to benefits sustainment
That all documented benefits are realized as planned and Governance board is consulted
Question 4:
You have been managing a program to deliver a new tractor that will use 75% less fuel. The program is ready for closure and to sustain the benefits, activities will be transitioned to the product support group. During this transition, you need to make sure that the
Program is perceived as successful
Final Estimation of the cost to sustain the benefits are completed
Program is accepted and formally closed
Component transition requests have been submitted.
Question 5:
As a program manager of an international program that banks on contractors for approximately 80% of its work. Some of the contracts apply to a specific project, but 4 contracts span 7 of the projects. There is one basic ordering agreement, which enables the Program Manager to obtain temporary resources as required for this complex program. In terms of Program Procurement Administration, one should review the -
Program reports
Procurement register
Contract management plan
Change requests
Question 6:
You are a program manager for an ERP software services company. This new software will bring your company into ERP Cloud computing. It also will replace your company's legacy finance and accounting systems. To formalize scope, you should use the -
PWBS
Program Charter
Business case
Financial framework
Question 7:
It is important to control the scope changes on programs to ensure successful program completion. These scope changes can originate from many sources including -
Risks
Architecture issues
Missed milestones
Resources reallocations
Question 8:
You have been selected to head all of eLearning and have been told to launch a program to develop new media for delivering your company's content. The program has a number of stakeholders, some of whom are supportive and some of who are sceptical and you anticipate many debates concerning the program's objectives. As the program manager, you recognize that you need to rely on -
Leadership skills
Conflict resolution skills
Diplomatic Skills
Environment awareness skills
Question 9:
Working on your program to improve the economic growth of your country, you know from the business case there are many risks and issues. However, the business case only presented a high-level view of them. You then held a risk planning meeting with your stakeholders to help prepare a risk management plan and you have set up a process to track issues. Now, you and your core program team are working to identify risks that could affect your program team are working to identify risks that could affect your program building on those in the business case. You and your team are clarifying the definition of each risk and grouping them by cause. This means you are using which of the following techniques?
Flowcharts
Influence diagrams
Root cause identification
SWOT analysis
Question 10:
You are enjoying your work as the program manager for the new ice cream program in MNC, which is so well known around the world for its cereal products. All resources are being provided internally and everyone on the team is signing a confidentiality agreement so competitors are not aware of this new program. However, already resources are scarce in the organization working on cereal products. You have prepared your schedule and in doing had assumed that the needed resources would be available. However, in a meeting with your Governance Board, you now realize you will need to do a lot of negotiation for resources. Fortunately, you have been successful and as a result, three experienced project managers got assigned and who are now supporting the three projects in the program. It is important that now since these Project Managers are assigned that you evaluate their performance according to the -
Resource Plan
Program management plan
Benefits realization plan
Project Plan
Question 11:
As the program manager for a new course curriculum of training products, one will need to work with numerous divisions within the company, many of which are located in other countries. Additionally, other projects and programs in the organization are linked to your program at various levels. Because you realize the importance of gate reviews and health checks, you need to develop a (n) -
Interface management plan
Integration plan
Governance plan
Program roadmap
Question 12:
A private college in Delhi is planning to upgrade its operating system to Windows 8 . The key benefit is improved employee performance, better dashboards, touch screen capabilities. There are several conflicts especially between IT and the Counsellor's wing. The Governance Board is more concerned about Funding and the Top Management being kept happy. Budget cuts are likely to be certain. Training for each of the department is on the critical path. Governance Board has put this as a High Risk since any delay in training can impact the Program Timelines and budget and at the same time low quality of training impedes the attainment of Program Objective. You come with a plan of Online training course in addition to combined in class training. You have found a vendor from Brazil who will develop training materials at a low cost. This is an example of
Risk Mitigation: Reducing Probability of delays as well as the impact
Risk Avoidance strategy
Risk Acceptance Strategy
Insurance
Question 13:
Energy saving program has a return 1Million /year for 3 years. What is the NPV if it costs $2.3 Million today at 10%?
$0.32 Million
$-0.26 Million
+$0.28 Million
+0.19 Million
Question 14:
A Program has 75 Stakeholders this week. Next week another 25 more are getting added. How many channels more will get increased next week from communication perspectives?
175
4950
2175
2775
Question 15:
Your program exceeded cost due to underestimation of resource costs, while arriving at cost baseline. PV= $150000, EV = $100000, AC = $140000. You expect the underestimation to impact in the future as well. If the value of balance work (BAC-EV) is $120000, then what would be the EAC (Estimate at Completion)?
$3,08,000
$2,60,000
$1,68,000
$3,00,000
Question 16:
Most of the projects in our program have reached the closing stage. What is the order that should be followed to close our Program & the projects finally, within the Program?
Close project, close program, close program contract
Close project, Close program contract, close program
Close program, close project, close program contract
Close project, close project contract, close program contract
Question 17:
Nancy is managing a Program “Health Care” for the Government which requires them to procure certain chemicals in bulk. The Government policies are very strict in terms of managing procurements. She has requested RFI, feasibility studies, trade studies and market analysis. Sponsor calls for a meeting and asks her about the process she is currently performing in her program. What process is she in?
Draft Contract
Program Procurement Planning
Select Sellers
Program Communication Planning